## Dashboard
Halcyon Credit — Daily Progress Dashboard
Agentic Underwriting Copilot · Sprint 0 → Sprint 4 · Owner: Yash Gupta
Last updated: 2026-06-22
KEY METRICS
Current Sprint |  | Sprint Progress |  | Total Stories |  | Stories Done
Sprint 0 |  | 0% |  | 54 |  | 2
Open Blockers |  | Pending Tasks |  | High Priority Items |  | Days into Project
1 |  | 8 |  | 3 |  | 0
SPRINT PROGRESS
Sprint | Goal | Planned pts | Done pts | % Complete | Status
Sprint 0 | Discovery, planning, de-risking | 34 | 16.5 | 48.53% | In Progress
Sprint 1 | POC — end-to-end thin slice | 39 | 0 | 0% | Not Started
Sprint 2 | Multi-scheme policy + ML hardening | 47 | 0 | 0% | Not Started
Sprint 3 | Doc verify, regulatory, fairness | 47 | 0 | 0% | Not Started
Sprint 4 | Audit, guardrails, pilot | 50 | 0 | 0% | Not Started
TODAY’S SNAPSHOT (pulls latest row from Daily Log)
Date | Sprint | Planned % | Actual % | Top tasks done | Active blockers | Owner
2026-06-22 | Sprint 0 | 40% | 48% | PRD v2.0 finalised; full Agile backlog authored (15 epics, 54 stories, 217 pts); Sprint 0–4 plan; repo initialised; A-8b drafted | 3 | Yash, Abe, Het

## Daily Log
Date | Sprint | Planned % | Actual % | Tasks Completed Today | Hours Spent | Blockers Raised | Owner | Notes
2026-06-22 | Sprint 0 | 40% | 48% | PRD v2.0 finalised; full Agile backlog authored (15 epics, 54 stories, 217 pts); Sprint 0–4 plan; repo initialised; A-8b drafted | 8 | A-8b signoff; vector store choice; wireframes | Yash, Abe, Het | Sprint 0 baseline pushed to repo

## Blockers
Blocker ID | Date Raised | Description | Severity | Owner | Workarounds Tried | Status | Resolution / Next Step | Date Resolved
BL-001 | 2026-06-22 | A-8b (CODE_GENDER / DAYS_BIRTH exclusion) not yet signed off by Compliance SME | High | Yash | Drafted the exclusion note ourselves and shared on Slack; treating as confirmed pending writeback | Open | Need 10 min with Compliance SME tomorrow morning
BL-002 | 2026-06-22 | Vector store choice (Chroma vs Pinecone) blocking HL architecture + DB schema | High | Yash | Built back-of-envelope cost model for both at 200 apps/hr — Chroma ~30% cheaper, needs self-hosting | In Progress | 15-min call with Tech Lead to decide before Sprint 1
BL-003 | 2026-06-22 | Wireframes not started — UX designer pulled to another project | Medium | UX | Sketched low-fi flow on paper (Queue → App Detail → Evidence Panel → Decision) | Open | Reassign UX bandwidth tomorrow

## Pending Tasks
Task ID | Title | Sprint | Epic | Owner | Due Date | % Complete | Status | Priority | Notes
US-006 | End-to-End User Flow Definition | Sprint 0 | EPIC-12 | UX | 2026-06-23 | 20% | In Progress | High | Paper sketch done; needs digitisation
US-007 | Wireframes / Mockups | Sprint 0 | EPIC-12 | UX | 2026-06-23 | 0% | Not Started | Medium | Blocked by BL-003
US-008 | Technical Feasibility Analysis | Sprint 0 | EPIC-15 | Abe, Yash, Het | 2026-06-23 | 20% | In Progress | High | Cost model started, latency budget pending
US-009 | High-Level Architecture | Sprint 0 | EPIC-15 | Yash | 2026-06-23 | 15% | In Progress | High | Blocked by BL-002
US-010 | DB Design Planning | Sprint 0 | EPIC-10 | Abe | 2026-06-23 | 10% | In Progress | High | Awaiting vector store decision
US-011 | API Contract (OpenAPI) | Sprint 0 | EPIC-15 | Yash | 2026-06-23 | 0% | Not Started | High | Depends on US-009
US-005 | A-8b Open-Question Closure | Sprint 0 | EPIC-15 | Abe | 2026-06-23 | 40% | In Progress | High | Blocked by BL-001
US-015 | DoR & DoD | Sprint 0 | EPIC-15 | Abe | 2026-06-23 | 70% | In Progress | Medium | DoR list pending
US-003 | Stakeholder Discussions | Sprint 0 | EPIC-12 | Abe, Yash, Het | 2026-06-23 | 30% | In Progress | High | Interviews to schedule
US-004 | PRD Review & Validation | Sprint 0 | EPIC-15 | Yash, Het | 2026-06-23 | 60% | In Progress | High | Formal signoff record pending

## High Priority
Item | Type | Owner | Due Date | Status | Why it matters | Next Action
A-8b signoff from Compliance SME | Decision | Yash | 2026-06-23 | Open | Unblocks ML feature engineering for Sprint 1 | 10-min call with SME tomorrow AM
Vector store choice (Chroma vs Pinecone) | Decision | Tech Lead | 2026-06-23 | Open | Drives architecture, DB schema, cost model | 15-min call with Tech Lead
Reassign UX bandwidth for wireframes | Resource | PM | 2026-06-23 | Open | Sprint 0 cannot close without 4 wireframes | Discuss with PM in standup
Publish OpenAPI v0.1 | Deliverable | Yash | 2026-06-23 | Not Started | Backend + UI can parallelise from Sprint 1 | After US-009 closes
RAG retrieval accuracy spike plan | Risk | DS | 2026-06-24 | Open | ★ riskiest PRD assumption (Risk R-1) | Draft 30-scenario eval set

## Sprint Tracker
Sprint | Goal | Planned pts | Done pts | % Complete | # Stories | # Done | Start | End | Status
Sprint 0 | Discovery, planning, de-risking | 34 | 16.5 | 48.53% | 15 | 2 | 2026-06-22 | 2026-06-28 | In Progress
Sprint 1 | POC — end-to-end thin slice | 39 | 0 | 0% | 11 | 0 | 2026-06-29 | 2026-07-05 | Not Started
Sprint 2 | Multi-scheme policy + ML hardening | 47 | 0 | 0% | 9 | 0 | 2026-07-06 | 2026-07-19 | Not Started
Sprint 3 | Doc verify, regulatory, fairness | 47 | 0 | 0% | 9 | 0 | 2026-07-20 | 2026-08-02 | Not Started
Sprint 4 | Audit, guardrails, pilot | 50 | 0 | 0% | 10 | 0 | 2026-08-03 | 2026-08-16 | Not Started

## Backlog
Product Backlog — 54 user stories (reference, edit Status / Owner / % freely)
Story | Title | Epic | Sprint | Pts | Priority | Owner | Status | % Complete
Story | Title | Epic | Sprint | Pts | Priority | Owner | Status | % Complete
US-001 | Functional Requirement Gathering | EPIC-15 | Sprint 0 | 3 | High | Abe | In Progress | 75%
US-002 | Business Requirement Analysis | EPIC-15 | Sprint 0 | 3 | High | Yash, Het | In Progress | 70%
US-003 | Stakeholder Discussions | EPIC-12 | Sprint 0 | 3 | High | Abe, Yash, Het | In Progress | 30%
US-004 | PRD Review & Validation | EPIC-15 | Sprint 0 | 2 | High | Yash, Het | In Progress | 60%
US-005 | Requirement Clarification (A-8b) | EPIC-15 | Sprint 0 | 2 | High | Abe | In Progress | 40%
US-006 | User Flow Definition | EPIC-12 | Sprint 0 | 3 | High | UX | In Progress | 20%
US-007 | Wireframes / Mockups | EPIC-12 | Sprint 0 | 3 | Medium | UX | Not Started | 0%
US-008 | Technical Feasibility | EPIC-15 | Sprint 0 | 3 | High | Abe, Yash, Het | In Progress | 20%
US-009 | HL Architecture | EPIC-15 | Sprint 0 | 3 | High | Yash | In Progress | 15%
US-010 | DB Design Planning | EPIC-10 | Sprint 0 | 3 | High | Abe | In Progress | 10%
US-011 | API Contract Definition | EPIC-15 | Sprint 0 | 3 | High | Yash | Not Started | 0%
US-012 | Risk Register | EPIC-15 | Sprint 0 | 2 | High | Het | In Progress | 85%
US-013 | Backlog Creation | EPIC-15 | Sprint 0 | 3 | High | Yash | Done | 100%
US-014 | Sprint Planning | EPIC-15 | Sprint 0 | 2 | High | Yash | Done | 100%
US-015 | DoR & DoD | EPIC-15 | Sprint 0 | 1 | High | Abe | In Progress | 70%
US-101 | Basic Auth | EPIC-14 | Sprint 1 | 3 | High |  | Not Started | 0%
US-102 | Basic Ingestion | EPIC-01 | Sprint 1 | 3 | High |  | Not Started | 0%
US-103 | Baseline ML Risk Score | EPIC-02 | Sprint 1 | 5 | High |  | Not Started | 0%
US-104 | Minimal Policy Corpus (5 clauses) | EPIC-03 | Sprint 1 | 2 | High |  | Not Started | 0%
US-105 | RAG Retrieval (single scheme) | EPIC-03 | Sprint 1 | 5 | High |  | Not Started | 0%
US-106 | POC Recommendation | EPIC-08 | Sprint 1 | 5 | High |  | Not Started | 0%
US-107 | Basic Underwriter UI | EPIC-12 | Sprint 1 | 5 | High |  | Not Started | 0%
US-108 | POC Audit Record | EPIC-10 | Sprint 1 | 3 | High |  | Not Started | 0%
US-109 | Mock Regulatory Stub | EPIC-06 | Sprint 1 | 3 | Medium |  | Not Started | 0%
US-110 | POC Demo Script | EPIC-15 | Sprint 1 | 2 | High |  | Not Started | 0%
US-111 | RAG Accuracy Spike (★) | EPIC-03 | Sprint 1 | 3 | High |  | Not Started | 0%
US-201 | Hardened ML AUC ≥ 0.80 | EPIC-02 | Sprint 2 | 8 | High |  | Not Started | 0%
US-202 | SHAP Top Contributors | EPIC-02 | Sprint 2 | 5 | High |  | Not Started | 0%
US-203 | Full 6-Scheme Policy Corpus | EPIC-03 | Sprint 2 | 5 | High |  | Not Started | 0%
US-204 | Multi-Scheme RAG + Source IDs | EPIC-03 | Sprint 2 | 5 | High |  | Not Started | 0%
US-205 | Retrieval Quality Monitoring | EPIC-13 | Sprint 2 | 5 | High |  | Not Started | 0%
US-206 | Multi-Scheme Policy Evaluator | EPIC-04 | Sprint 2 | 8 | High |  | Not Started | 0%
US-207 | Policy Versioning & Re-Index | EPIC-03 | Sprint 2 | 3 | Medium |  | Not Started | 0%
US-208 | Grounded Explanation Generation | EPIC-09 | Sprint 2 | 5 | High |  | Not Started | 0%
US-209 | PII Redaction Layer | EPIC-14 | Sprint 2 | 3 | High |  | Not Started | 0%
US-301 | Document Upload & Storage | EPIC-05 | Sprint 3 | 3 | High |  | Not Started | 0%
US-302 | Doc Completeness/Consistency | EPIC-05 | Sprint 3 | 8 | High |  | Not Started | 0%
US-303 | Regulatory Mock + Retry/Escalation | EPIC-06 | Sprint 3 | 8 | High |  | Not Started | 0%
US-304 | Fairness Audit + Hard Block | EPIC-07 | Sprint 3 | 8 | High |  | Not Started | 0%
US-305 | Proxy Leakage Assessment | EPIC-07 | Sprint 3 | 3 | Medium |  | Not Started | 0%
US-306 | Full HITL Escalation | EPIC-11 | Sprint 3 | 5 | High |  | Not Started | 0%
US-307 | Complete Evidence Chain | EPIC-08 | Sprint 3 | 5 | High |  | Not Started | 0%
US-308 | Override Capture | EPIC-11 | Sprint 3 | 3 | High |  | Not Started | 0%
US-309 | Evidence Panel UI | EPIC-12 | Sprint 3 | 5 | High |  | Not Started | 0%
US-401 | Immutable Audit | EPIC-10 | Sprint 4 | 8 | High |  | Not Started | 0%
US-402 | Cost Metering + Cutoff | EPIC-13 | Sprint 4 | 5 | High |  | Not Started | 0%
US-403 | Load Test & P95 Cert | EPIC-13 | Sprint 4 | 5 | High |  | Not Started | 0%
US-404 | Hallucination Eval Harness | EPIC-09 | Sprint 4 | 5 | High |  | Not Started | 0%
US-405 | Kill-Switch & Degraded Mode | EPIC-11 | Sprint 4 | 5 | High |  | Not Started | 0%
US-406 | Secrets & Least-Privilege | EPIC-14 | Sprint 4 | 3 | High |  | Not Started | 0%
US-407 | Ops Dashboard | EPIC-13 | Sprint 4 | 5 | High |  | Not Started | 0%
US-408 | Underwriter Pilot | EPIC-12 | Sprint 4 | 8 | High |  | Not Started | 0%
US-409 | Final AC Verification | EPIC-15 | Sprint 4 | 3 | High |  | Not Started | 0%
US-410 | Release Runbook | EPIC-15 | Sprint 4 | 3 | Medium |  | Not Started | 0%

## How to use
How to use this dashboard
Update every day:
1. Open the "Daily Log" sheet and add a new row at the bottom — fill date, sprint, planned %, actual %, tasks done today, hours, blockers raised, owner, notes.
2. Open "Blockers" and add any new blocker with severity, owner, workarounds tried, and status. Update existing blockers if status changes.
3. Open "Pending Tasks" — update % Complete and Status for tasks you touched today. Add new tasks as needed.
4. Open "High Priority" — add any items that need today’s attention (decisions to make, deliverables due, risks materialising).
5. (End of sprint) Open "Sprint Tracker" and update Done pts and # Done. The Dashboard KPIs and chart update automatically.
The "Dashboard" sheet pulls live KPIs and the latest Daily Log entry — no manual edits needed there.
Color key:
Green = Done / On Track
Yellow = In Progress
Red = Open blocker / Blocked / Overdue / At Risk
Gray = Not Started
Dropdowns (Status, Priority, Severity, Sprint, Type) are enforced via data validation — use the dropdown arrow when you click the cell.
Tabs:
• Dashboard — summary view (read-only-ish)
• Daily Log — add one row per day
• Blockers — register of issues
• Pending Tasks — active tasks across all sprints
• High Priority — today’s focus items
• Sprint Tracker — per-sprint roll-up
• Backlog — reference list of all 54 user stories